# Illinois State Water Survey (ISWS) COOPERATING TECHNICAL PARTNERS PROGRAM MANAGEMENT STATEMENT OF WORK PM SOW No. ISWS 25-01 Fiscal Year 2025

This page intentionally left blank

Table of Contents

Document Organization and Instructions	1

1.	Part 1 – Custom Statement of Work Information	2

1.1.	Project and Point of Contact Information	2

1.2.	Tasks and Deliverables to be Completed Under this SOW	3

1.3.	Schedule and Performance	19

1.4.	Guidelines and Standards	21

1.5.	Use of Contractors	21

1.6.	Reporting and Performance	22

1.7.	Privacy and Protection of Personally Identifiable Information	23

2.	Part 2 – Available PM Scope Activities	24

2.1.	State and Local Business Plans and/or Updates (Required)	25

2.2.	Global Program Management	25

2.3.	Global Outreach for Mapping	25

2.4.	Training to State, Local, Tribal, and Territorial Officials	26

2.5.	Mitigation Planning Technical Assistance	28

2.6.	Staffing	28

2.7.	Technical Pilot Projects	28

2.8.	Mentoring and Best Practices	28

2.9.	Minimal Map Printing	29

2.10.	Coordinated Needs Management Strategy	29

2.11.	Programmatic QA/QC Plan	30

2.12.	CTP Symposium	31

Authorized Representative Signatures	32

List of Tables	33

Acronyms	33

- Document Organization and Instructions

Cooperating Technical Partners (CTPs) should use this template to apply for an award to complete Program Management (PM) activities.

This document is organized into two parts. The goal is to simplify and streamline Statement of Work (SOW) completion and improve its use for both CTPs and the Federal Emergency Management Agency (FEMA).

Part 1 lists SOW elements that the CTP can customize (formatted in tables). These areas also contain required elements which cannot be modified:

Parts 1.1 – 1.3. In these sections, the CTP will describe the project and identify the scope elements to be completed under this SOW. The CTP can clarify or modify the standard descriptions and deliverables on fundable activities (as shown in Part 2). The CTP will also indicate the schedule for delivery, leverage, budget, performance measures and other related parts of the SOW.

Parts 1.4 – 1.7. These sections include standard language, to which the CTP is agreeing, that addresses standards, hiring contractors, reporting and performance, and protection of Personally Identifiable Information (PII). The CTP may not edit this language.

Part 2 provides standard language on scope activities that can be funded. If the CTP is applying for an individual fundable activity, they agree to the scope as written in Part 2 under that subsection unless otherwise noted in Part 1. CTPs can customize this language (by note/deliverable additions, subtractions, and other mechanisms) after each scope element in the “Custom Scope Elements” field. If the text is accepted as is, there is no need to copy text from Part 2 into Part 1. It is incorporated by reference.

Part 1 – Custom Statement of Work Information

In accordance with the CTP Partnership Agreement referenced in Table 1 between Illinois State Water Survey (herein referred to as “CTP”) and FEMA, the Program Management (PM) Statement of Work (SOW) No. ISWS 25-01 is as follows:

Project and Point of Contact Information

Instructions: Complete Table 1 with the basic project information and points of contact for both the CTP and FEMA staff.

Table 1. Project and Point of Contact Information

| Information Type | Insert Information |
| --- | --- |
| Project Name/Title (if applicable) | Program Management |
| CTP Organization Name: | Illinois State Water Survey |
| CTP Contractor Working on the activities in this SOW: Optional, only if contractors have already been identified; contractor support may be engaged for all activities except Staffing and Mentoring, which must be completed by the CTP | NA |
| Sub-Recipient Working on the activities in this SOW: Optional, only if sub-recipients have already been identified; contractor support may be engaged for all activities except Staffing and Mentoring, which must be completed by the CTPS | NA |
| CTP Partnership Agreement Date: | September 9, 2013 |
| Period of Performance: | 10/01/2025 to 9/30/2027 |
| CTP Project Manager: | Glenn Heistand |
| FEMA Regional Project Officer: When necessary, ask for FEMA assistance through the FEMA Regional Project Officer | John Wethington FEMA Region 5 |
| FEMA Funding to Complete this PM SOW: | $100,000 |
| CTP Estimated Leverage: Final leverage dollars or units will be entered as applicable in the Manage Data Development Task Workflow in the Mapping Information Platform (MIP). The leverage noted here is an estimate of leverage available at the time when the scope is prepared. It may be refined at any time in the project. See Estimating the Value of Partner Contributions to Flood Mapping Projects “Blue Book” (Blue Book) | NA |
| Project Team Coordination Activities: During the project, all members of the Project Team will coordinate, as needed, to see that activities, products and deliverables meet FEMA requirements and contain accurate, up-to-date information. | Meetings, teleconferences, and video conferences with FEMA and other Project Team members Monthly Telephone or video conversations with FEMA and other Project Team members, scheduled Monthly and as needed Email as needed As Necessary |

Tasks and Deliverables to be Completed Under this SOW

Narrative and Audience

Instructions: Complete Table 2 by providing a high-level narrative of the work to be done under this PM SOW, and the intended audience of the project.

Table 2. Narrative and Audience

| Information Type | Insert Information |
| --- | --- |
| SOW Narrative: | The State Business Plan is developed as a joint collaborative document between IDNR-OWR and ISWS, including Global Program Management Activities for Flood Risk Project Mapping Activities. Global Outreach for Mapping tasks is covered in the COMS SOW requested as part of the FFY25 grant. If COMS SOW is not initiated, then Global Outreach for Mapping tasks will need to be added to this PM SOM. Also, if FFY25 COMS SOW is not funded, PM SOW Mentoring and Best Practices task will need to have cost added. Coordinated Needs Management Strategy (CNMS) updates for Illinois are performed by ISWS. Programmatic QA/QC Plans are in place and updated as needed in response to changes in FEMA guidelines and specifications, internal workflow changes, and industry best practices. Project risks identified in the Mapping Activity Statements and CTP Performance Metrics under this grant will be reviewed quarterly and updates provided with the Quarterly Reports submitted through FEMA GO. The ISWS Coordinated Hazard and Mapping Program (CHAMP) staff carry out the tasks for FEMA projects. These staff are expected to earn and maintain Certification as Floodplain Managers (CFM). Maintaining the CFM status of CHAMP staff is part of the management performance and quality assurance protocols for the program. Other specialized certifications to maintain high quality performance standards include Professional Engineer, Geographic Information Systems Professional, and American Institute of Certified Planners. Continuing education credits must be earned annually to maintain certification. Attendance at Illinois Association for Floodplain and Stormwater Management (IAFSM), Illinois Geographic Information Systems Association (ILGISA), Association of State Floodplain Managers (ASFPM), American Planning Association (APA), National States Geographic Information Council (NSGIC), and other professional conferences, and FEMA training courses, conferences, workshops, and webinars provide the opportunity to earn required continuing education credits. |
| Intended Audience: | State of Illinois, including county and local jurisdictions contained therein., herein referred to as “community(ies)” |

Project Tasks and Deliverables

The following 12 tasks can be accomplished under this PM SOW:

State and Local Business Plans and/or Updates (required).

Global Program Management Activities (completed under the PM SOW when the CTP is also funded for tasks in the Flood Risk Project Mapping Activity Statement [MAS]).

Global Outreach for Mapping.

Training to State, Local, Tribal, and Territorial Officials.

Mitigation Planning Technical Assistance.

Staffing.

Technical Pilot Projects.

Mentoring and Best Practices.

Minimal Map Printing.

Coordinated Needs Management Strategy (CNMS).

Programmatic Quality Assurance/Quality Control (QA/QC) Plans.

CTP Symposium.

Note: The Staffing Task refers to the instance in which Staffing is the only PM task to be performed under this SOW (other than Business Plan, which is required). If the CTP is not performing Staffing, or is performing multiple activities that include Staffing, then the Staffing section of this SOW may not need to be filled out.

The sections below list these tasks and their associated deliverables.

Instructions: Please fill out the appropriate sections for the work you plan to complete. Required information includes 1) budget information, 2) what deliverables will be provided, and 3) descriptions of the detailed scope elements for each relevant task.

Funding information is required per task. In the leverage table for each task, please indicate the following:

A - FEMA Contribution. This is the funding FEMA is providing to the CTP to complete this PM SOW.

B - Partner Contribution. These are other required resources that the CTP will provide to complete the assigned activities for this PM SOW (also known as Leverage). Use Blue Book values or actual costs where Blue Book values do not exist. The current Blue Book is dated 2023. You can download it from FEMA’s Information Resource Library at: Estimating the Value of Partner Contributions to Flood Mapping Projects "Blue Book".

A+B – Total Project Cost The sum of A and B.

Task 1 - State and Local Business Plans and/or Updates (Required)

This task is required as a condition of PM funding – see Part 2.1.

Instructions: Add the required information to Table 3.

Table 3. Task 1 – State and Local Business Plans and/or Updates

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| State and Local Business Plans and/or Updates (required as a condition of PM funding) (see Part 2.1) | ☒ | $30,000 | $0 |  | $30,000 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Business Plan (required) |  |  |  | ☒ |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.1. If you accept the text as is, you do not need to copy the wording here. Detail here only what you plan to change. Indicate here if the Community Outreach and Mitigation Strategies (COMS) Engagement Plan and PM Business Plan will be combined as a single deliverable. ISWS will collaborate with the Illinois Department of Natural Resources/ Office of Water Resources (IDNR/OWR) a CTP, to prepare a joint business plan for the State of Illinois. |  |  |  |  |  |

Task 2 – Global Program Management Activities (to be completed under the PM SOW when the CTP is also funded for tasks in the Flood Risk Project MAS)

This task will be completed under the PM SOW when the CTP is also funded for tasks in the Flood Risk Project MAS – see Part 2.2.

Instructions: Add the required information to Table 4.

Table 4. Task 2 – Global Program Management Activities

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Global Program Management Activities (to be completed under the PM SOW when the CTP is also funded for tasks in the Flood Risk Project MAS) (see Part 2.2) | ☒ | $30,000 | $0 |  | $30,000 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Global Program Management Plan |  |  |  | ☒ |  |
| Other: Updated project risk assessments and CTP Performance Metrics included in quarterly reports. |  |  |  | ☒ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.2. If you accept the text as is, you do not need to copy the wording here. Enter any other deliverables planned to be developed in the “Other” field above. Detail what will be completed in this activity in this section. Global Program Management Plan will be integrated in the Business Plan |  |  |  |  |  |

Task 3 – Global Outreach for Mapping

Task 3 can be selected under this task if there is no COMS SOW. If a COMS SOW is also completed, the Outreach Plan is required under the Strategic Planning for Community Engagement Task and should not be part of this PM SOW.

Instructions: Add the required information to Table 5.

Table 5. Task 3 – Global Outreach for Mapping

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Global Outreach for Mapping (see Part 2.3) | ☐ | $0 | $0 |  | $0 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Outreach Plan |  |  |  | ☐ |  |
| Report detailing outreach and coordination activities including backup or supplemental information used in writing the report |  |  |  | ☐ |  |
| Business Plan update describing (in detail) the outreach activities |  |  |  | ☐ |  |
| Updates to CTP’s website |  |  |  | ☐ |  |
| Other: COMS SOW is being requested as part of the FFY24 grant. If COMS SOW is not initiated, then Global Outreach for Mapping tasks will need to be added to this PM SOM. |  |  |  | ☒ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.3. If you accept the text as is, you do not need to copy the wording here. Detail here only what you plan to change. Task 3 – Global Outreach for Mapping will be covered under Communication and Outreach to Communities task in COMS SOW. The Illinois Association for Floodplain and Stormwater Management (IAFSM) conducts workshops and conferences as well as providing a bi-monthly newsletter. Community officials and engineers who represent communities look to IAFSM for leadership in floodplain management and flood risk mitigation. ISWS staff support IAFSM serving as officers and committee chairs. ISWS staff contribute articles to the newsletter and present at workshops and conferences providing training, education, and updates to communities and engineers on FEMA standards, products, and best practices. ISWS has a booth at the annual Illinois conference to demonstrate FEMA products developed in Illinois. ISWS staff in this leadership role are recognized as experts in flood hazard identification and risk management, developing and maintaining relationships with community leaders and professionals involved with floodplain and stormwater management. ISWS staff participate in the Rapid Assistance Flood Team (RAFT) deployment supported by IAFSM assisting local floodplain managers with post disaster damage assessments. ISWS staff are active in the Illinois Geographic Information Systems Association (ILGISA). ISWS staff serve as officers and assist with annual conferences. ISWS has a booth at conferences to demonstrate FEMA products as well as presenting FEMA projects. Communities send GIS staff to this conference, and this provides an opportunity to educate them about FEMA GIS products, in particular the DFIRM geodatabase and Flood Risk Database. The Association of State Floodplain Managers (ASFPM) is a national organization of professionals interested in floods, floodplain management and related topics. IAFSM is a state Chapter of ASFPM. ISWS staff support ASFPM activities in a variety of ways including serving as officers, on committees, presenting through hosted webinars and at the national conference. The American Planning Association (APA) is a professional organization representing the field of planning in the United States. APA activities work to provide leadership by advocating excellence in community planning, promoting education and citizen empowerment, and providing the tools and support necessary to meet the challenges of growth and change. In addition, involvement with the Association of Collegiate Schools of Planning (ACSP) supports academic and research excellence in planning education, fostering collaboration among planning scholars, students, and institutions to advance the field through scholarship, teaching, and service. ISWS staff engage with Esri products to create FEMA RiskMAP products. ISWS staff are active with Esri through training, and presentations at Esri-sponsored events such as the Esri User Conference. These interactions help ensure that FEMA GIS products are compatible with Esri platforms and that users are equipped with the knowledge to apply these tools effectively in flood risk management. ISWS has a booth at the Annual Illinois Emergency Management Agency Training Summit and participates in regional trainings. The National States Geographic Information Council (NSGIC), a leading professional organization, fosters geospatial awareness and advocacy by leveraging the power of GIS and location-based information. By harnessing water and flood data, educational resources, and cutting-edge mapping tools, NSGIC supports informed decision-making. Our team at ISWS benefits from active participation and specialized training through NSGIC, enhancing our flood mapping products. ISWS maintains a web site hosting RiskMAP and other outreach products including reports and geodatabases, studies that are in progress, and providing links to relevant FEMA web sites. |  |  |  |  |  |

Task 4 – Training to State, Local, Tribal, and Territorial Officials

Instructions: Add the required information to Table 6.

Table 6. Task 4 – Training to State, Local, Tribal, and Territorial Officials

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Training to State, Local, Tribal, and Territorial Officials (see Part 2.4) | ☐ |  |  |  |  |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.4. If you accept the text as is, you do not need to copy the wording here. Enter any other deliverables planned to be developed in the “Other” field above. Detail the training and/or audiences associated with this activity in this section. {enter custom scope elements} |  |  |  |  |  |

Task 5 – Mitigation Planning Technical Assistance

Instructions: Add the required information to Table 7.

Table 7. Task 5 – Mitigation Planning Technical Assistance

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Mitigation Planning and Technical Assistance (TA) (see Part 2.5) | ☐ |  |  |  |  |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| A report detailing the TA provided including date(s) of TA and type of assistance and State, Local, Tribal, and Territorial community stakeholders supported |  |  |  | ☐ |  |
| Copies of all technical data provided to State, Local, Tribal, and Territorial communities |  |  |  | ☐ |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.5. If you accept the text as is, you do not need to copy the wording here. Enter any other deliverables planned to be developed in the “Other” field above. Detail the technical assistance that will be completed in this activity in this section. {enter custom scope elements} |  |  |  |  |  |

Task 6 – Directly Funded Staffing

Instructions: Add the required information to Table 8.

If Staffing is the only PM Task to be performed under this SOW, please complete Table 15 and Table 16 below.

Table 8. Task 6 – Directly Funded Staffing

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Directly Funded Staffing (see Part 2.6) | ☐ |  |  |  |  |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| {Insert number of staff} will attend regional mapping meetings hosted by FEMA regions |  |  |  | ☐ |  |
| Maintain {Insert number of staff}; potentially engage {Insert number of staff} current personnel to support CTP program activities |  |  |  | ☐ |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.6. If you accept the text as is, you do not need to copy the wording here. Still, detail here the activities and tasks that are planned for staff and need to be funded. {enter custom scope elements} |  |  |  |  |  |

Task 7 – Technical Pilot Projects

Instructions: Add the required information to Table 9.

Table 9. Task 7 – Technical Pilot Projects

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Technical Pilot Projects (see Part 2.7) | ☐ |  |  |  |  |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note, given that pilot activities are (by definition) new, there are no details of the scope written in Part 2.7. Enter deliverables planned to be developed in the “Other” field above. Detail what will be completed in this activity in this section. {enter custom scope elements} |  |  |  |  |  |

Task 8 – Mentoring and Best Practices

Instructions: Add the required information to Table 10.

Table 10. Task 8 – Mentoring and Best Practices

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Mentoring and Best Practices (see Part 2.8) | ☐ | $0 | $0 |  | $0 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| List of existing or potential CTP entities to be mentored |  |  |  | ☐ |  |
| Schedule and explanation of Mentoring activities |  |  |  | ☐ |  |
| Report detailing Mentoring activities provided |  |  |  | ☐ |  |
| Participant Surveys completed by mentored individuals providing feedback on the quality and benefits of the mentor(s) and Mentoring activities |  |  |  | ☐ |  |
| {Insert #} Best Practice write-ups to be shared nationally on the CTP Collaboration Center, on the CTP Mentoring Network (via Basecamp), and with FEMA Regional Project Officer |  |  |  | ☐ |  |
| Other: {Insert additional details} |  |  |  | ☒ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.8. If you accept the text as is, you do not need to copy the wording here. Detail here only what you plan to change. If FFY24 COMS SOW is not funded, this PM SOW Mentoring and Best Practices task will need to have cost added. |  |  |  |  |  |

Task 9 – Minimal Map Printing

Instructions: Add the required information to Table 11.

Table 11. Task 9 – Minimal Map Printing

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Minimal Map Printing (see Part 2.9) | ☐ |  |  |  |  |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Quarterly report detailing the map printing activities including recipient community/individual, panel number, number of copies, and total associated cost |  |  |  | ☐ |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.9. If you accept the text as is, you do not need to copy the wording here. Detail here only what you plan to change. {enter custom scope elements} |  |  |  |  |  |

Task 10 – Coordinated Needs Management Strategy

Instructions: Add the required information to Table 12.

Table 12. Task 10 – Coordinated Needs Management Strategy

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Coordinated Needs Management Strategy (CNMS) (see Part 2.10) | ☒ | $30,000 | $0 |  | $30,000 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Interim deliverables for the mapping project along its life cycle (funded, Preliminary, Letter of Final Determination [LFD]) |  |  |  | ☐ |  |
| Supporting documentation for new determinations |  |  |  | ☐ |  |
| A self-certification document outlining the funded scope and comments per region discretion |  |  |  | ☐ |  |
| A self-certified CNMS spatial database using the CNMS QC tool |  |  |  | ☐ |  |
| Other: QC and Incorporation opf Validation Assessments |  |  |  | ☒ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.10. If you accept the text as is, you do not need to copy the wording here. Detail here only what you plan to change. {enter custom scope elements} |  |  |  |  |  |

Task 11 – Programmatic Quality Assurance/Quality Control Plans

Instructions: Add the required information to Table 13.

Table 13. Task 11 – Programmatic QA/QC Plans

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| Programmatic Quality Assurance/Quality Control (QA/QC) Plans (see Part 2.11) | ☒ | $10,000 | $0 |  | $10,000 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Programmatic QA/QC Plan that includes any updates |  |  |  | ☒ |  |
| Quarterly report detailing the QA/QC activities completed for flood mapping products |  |  |  | ☐ |  |
| Corrective Action Plan(s) as needed |  |  |  | ☐ |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.11. If you accept the text as is, you do not need to copy the wording here. Detail here only what you plan to change. ISWS QA/QC Plans and Checklists Professional development activities to support staff Certified Floodplain Manager (CFM) credentials are important to maintain up-to-date knowledge of the FEMA program, guidelines and specifications, and appropriate QA/QC plans and checklists. |  |  |  |  |  |

Task 12 – CTP Symposium

Instructions: Add the required information to Table 14. Task 12 – CTP Symposium.

Table 14. Task 12 – CTP Symposium

| PM Task | Mark “X” if task will be done under this SOW | (A) FEMA Contribution | (B) Partner Contribution |  | (A+B) Total Project Cost |
| --- | --- | --- | --- | --- | --- |
| CTP Symposium (see Part 2.12) | ☐ | $0 | $0 |  | $0 |
| Deliverable |  |  |  | Mark “X” if deliverable will be done under this task |  |
| Travel to and attend the CTP Symposium at request of FEMA region |  |  |  | ☐ |  |
| Other: {Insert additional details} |  |  |  | ☐ |  |
| Custom Scope Elements |  |  |  |  |  |
| Note that if you do not modify this cell, you agree to the scope as written in Part 2.12. ENTER any planned deliverables in the “Other” field provided above. Specific scope elements that will be completed in this activity can be added here. {enter custom scope elements} |  |  |  |  |  |

Percentage of Time Spent on Tasks or Activities

Instructions: Table 15 and Table 16 are only required if Staffing is the only PM Task to be performed under this SOW (other than the State/Local Business Plan, which is required). If the CTP is not performing Staffing or is performing multiple activities that include Staffing, these tables may not be needed. Coordinate with your FEMA Regional Project Officer about any other uses.

Note: Assume each staff member works 100% of their day on this project. This represents percentage of total time on the project, not the hours spent.

Table 15. Percentage of Time Spent on Tasks for Funded Staff

| Task | Funded Staff Member 1 | Funded Staff Member 2 | Funded Staff Member 3 | Funded Staff Member 4 | Brief Work Description Across All Funded Staff |
| --- | --- | --- | --- | --- | --- |
| Program Management | % | % | % | % |  |
| Outreach for Mapping | % | % | % | % |  |
| Training to State, Local, Tribal, and Territorial Officials | % | % | % | % |  |
| Mitigation Planning Technical Assistance | % | % | % | % |  |
| Mentoring and Best Practices | % | % | % | % |  |
| {Insert additional activities} | % | % | % | % |  |
| Total (not to exceed 100% per employee) |  |  |  |  |  |

Table 16. Percentage of Time Spent on Tasks for Unfunded Staff

| Task | Unfunded Staff Member 1 | Unfunded Staff Member 2 | Unfunded Staff Member 3 | Unfunded Staff Member 4 | Brief Work Description Across All Unfunded Staff |
| --- | --- | --- | --- | --- | --- |
| Technical Engineering and Mapping | % | % | % | % |  |
| Hazard Mitigation | % | % | % | % |  |
| Risk Assessment | % | % | % | % |  |
| Outreach | % | % | % | % |  |
| Program Management and Overseeing Contracts | % | % | % | % |  |
| {Insert additional activities} | % | % | % | % |  |
| Total (not to exceed 100% per employee) |  |  |  |  |  |

Schedule and Performance

Instructions: Insert each deliverable for all activities included in this PM SOW in Table 17. PM Task Deliverables Schedule. Examples are provided in italics in the first row. Deliverables can be listed individually or grouped by a single deliverable date. Add more rows to the table as needed. Due dates will be discussed with the FEMA Regional Project Officer.

Table 17. PM Task Deliverables Schedule

| SOW Activities | Deliverable | Deliverable Due Date | Submitted To |
| --- | --- | --- | --- |
| Business Plan (required) | Business Plan | Ex. two months from award date | Ex. FEMA Regional Project Officer |
| Global Program Management | Program Management Plan | 4 months from Award date | FEMA Regional Project Officer |
| CNMS | CNMS spatial database updates | Regularly through grant period | Regional CNMS database |
| Programmatic QA/QC | Programmatic QA/QC Plan | 5 months from Award date | FEMA Regional Project Officer |

The activities documented in this SOW will be completed in accordance with Table 17. PM Task Deliverables Schedule. If this schedule needs to change, the CTP will coordinate with the FEMA Regional Project Officer and other necessary Mapping Partners as soon as possible. Deliverables must be uploaded to the MIP unless otherwise approved by the FEMA Regional Project Officer. The CTP must upload final deliverables to the MIP before the period of performance ends.

Note: Performance measures are parameters captured to track project performance. The CTP Performance Measures Matrix, included in the Appendix of the Notice of Funding Opportunity (herein referred to as the funding opportunity), shows how project details and action items can be used to demonstrate a project aligns with its stated goals.

Identify the appropriate performance measures in Table 18 based on the document “2025 CTP Performance Measures Matrix.” Coordinate with your FEMA Regional Project Officer.

Delete this instructional note before application submission.

Table 18. Performance Measures Targets

| Outcome and Output Measure (from NOFO) | Output Measurement (with customized Target) | Recorded Unit/Scale |
| --- | --- | --- |
| Outcome: Advancement of program metrics and/or accomplishment of project performance measures, captured as Earned Value Output Measure: SPI Threshold (final) | Report on Schedule Performance Index (SPI). Must be between 0.92 and 1.08. If it is not, provide information on what is being done to correct the problem. | SPI Ratio (Budgeted Cost of Work Performed/Budgeted Cost of Work Scheduled [planned]) |
| Outcome: Advancement of program metrics and/or accomplishment of project performance measures, captured as Earned Value Output Measure: CPI Threshold (final) | Report on Cost Performance Index (CPI). Must be between 0.92 and 1.08. If it is not, provide information on what is being done to correct the problem. | CPI ratio (Budgeted Cost Work Performed/ Actual Cost Work Performed) |
| Continued maintenance (using non-federal funds) | 0.5 FTE non-federal support. See Business Plan for activities. | Should be expressed as either "Achieved" or "Not Achieved". |
| {Insert Outcome and Output Measure} | {Insert Output Measurement Option (customized)} | {Insert Recorded Unit/Scale} |
| {Insert Outcome and Output Measure} | {Insert Output Measurement Option (customized)} | {Insert Recorded Unit/Scale} |

Guidelines and Standards

The standards relevant to this SOW are presented in FEMA Policy 204-078-1 Standards for Flood Risk Analysis and Mapping, Revision 14.

This Policy supersedes all previous standards in the Guidelines and Specifications for Flood Hazard Mapping Partners. This includes all related appendices and procedure memoranda. Find more information and links to guidance documents, technical references, templates, and other resources that support these standards on the FEMA Guidelines and Standards website. This is at: Guidelines and Standards for Flood Risk Analysis and Mapping Activities Under the Risk MAP Program. FEMA reviews standards each year. Please use the most current version of the policy.

For any Mitigation Planning Technical Assistance activities, coordinate with the FEMA Regional Project Officer to confirm compliance with regional requirements. Additional information is available in FEMA’s Incorporating Mitigation Planning Technical Assistance guidance document, available on the FEMA Guidelines and Standards website at: Guidance for FEMA's Risk Mapping, Assessment and Planning.

For CNMS activities, all work will be performed in accordance with the requirements specified in the most recent CNMS Technical Reference available at: Technical References for Flood Risk Analysis and Mapping.

Use of Contractors

Check the applicable statement in Table 19.

Table 19. Use of Contractors

| Select One | Description of Contractor Options |
| --- | --- |
| ☐ | Contractor support may be engaged for all activities within this SOW, except Staffing and Mentoring, which must be completed by the CTP. The CTP will identify the name of the CTP contractor for services engaged as part of this SOW. The CTP will ensure that the procurement for all contractors used for this Program Management Activity complies with the requirements of Title 2 Code of Federal Regulations (CFR) Part 200 - Part 200 - Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards. Guidance provided in this part includes, but is not limited to, contract administration and recordkeeping, notification requirements, review procedures, competition, methods of procurement, and cost and pricing analysis. Refer to Title 2 CFR Part 200. Additionally, contractors must not pose a conflict-of-interest issue. |
| ☒ | The CTP does not intend to engage the services of a contractor for this SOW. No transfer of funds to agencies, other than those identified in the approved cooperative agreement application, will be made without prior approval from FEMA. The CTP will ensure that the procurement for all contractors, if any are engaged for this SOW, complies with the requirements of Title 2 CFR Part 200 - Part 200 - Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards. Guidance provided in this part includes, but is not limited to, contract administration and recordkeeping, notification requirements, review procedures, competition, methods of procurement, and cost and pricing analysis. Refer to Title 2 CFR Part 200. |

Reporting and Performance

Financial Reporting: Because FEMA has provided funding to the CTP, financial reporting requirements for the CTP will be set by the terms of the funding opportunity, Articles of Agreement, or Award Notice for this SOW. The CTP will also refer to Title 2 CFR Part 200. The CTP will provide financial reports to the FEMA Regional Project Officer and Assistance Officer per the terms of the signed Cooperative Agreement for this SOW.

Performance Reporting: CTPs must provide a signed performance report (using the list of required information shown in the funding opportunity). The CTP will submit the report quarterly during the period of performance. Reports will be required for partial calendar quarters and periods when no grant award activity occurs. An old Standard Form-Performance Progress Report (SF-PPR) may be substituted for the performance report, if preferred. The CTP will refer to Title 2 CFR Part 200 for the minimum requirements for progress reporting. The FEMA Regional Project Officer, as needed, may request additional information on progress.

The CTP will meet with FEMA and/or its contractor(s) as frequently as needed to review the progress of the project. These meetings are in addition to the quarterly financial and status submittals. These meetings may alternate between the FEMA Regional Office, the CTP office and conference calls as necessary.

The CTP must report performance of the grant along with the progress reports. Table 18. Performance Measures Targets shows which performance measures the CTPs will use to track performance. If you are completing a COMS/PM project alongside a Flood Risk Project MAS, use the relevant measures in the 2025 CTP Performance Measures Matrix. Quantitative Targets for performance measures are defined using the 2025 CTP Performance Measures Matrix in conjunction with your FEMA Regional Project Officer and those defined in Table 18.

CTPs are responsible for entering their quarterly performance of each measure into the CTP Performance Measures Reporting Tool (Tool) each quarter, unless otherwise directed by their FEMA Regional Project Officer. Each output measurement identified above must have a quarterly performance reported in the Tool within one month of the end of the quarter. Quarterly performance data can be exported from the Tool and attached to the Quarterly Report that must be uploaded to FEMA Grants Outcomes.

Earned Value Data Entry:

The CTP must report on the earned value of projects that are in the MIP each month. They must explain variances outside of the tolerance defined in Table 18. The FEMA Regional Offices must initiate and create a Corrective Action Plan (CAP) when a CTP is outside of the tolerance. The CTP is required to implement this CAP as instructed by their FEMA Regional Office. A CAP must define the reason for the variance and the intended resolution. FEMA Regional Offices will coordinate with FEMA Headquarters when CAPs are developed.

COMS SOW/PM SOW tasks are now tracked in the MIP. Cost and schedule performance measures are defined in this SOW. These measures will be used to monitor CTP performance and to determine future funding eligibility. Earned Value data entry involves the CTP updating cost, schedule and performance (physical % complete) in the MIP each month for each assigned task. The CTP may contact the FEMA Regional Office to obtain additional guidance (as needed) for updating COMS/PM efforts in the MIP.

Privacy and Protection of Personally Identifiable Information

A CTP’s organizational access to the MIP provides you access to PII. Please have your organization coordinate with the FEMA Regional Office. Each user must currently meet the new Risk Analysis Management (RAM) Access Portal (RAP) process requirements.

Please contact your FEMA Regional Project Officer for more information.

Part 2 – Available PM Scope Activities

Note, unless otherwise noted in the Custom Scope Elements cell(s) in Tables 3-14 in Part 1.2.2, the CTP will fulfill all scope requirements identified in the following tasks.

The activities outlined in this SOW will be completed as specified in the funding opportunity, Award Notice, and/or Articles of Agreement. The SOW may be terminated at the option of FEMA or the CTP in accordance with the provisions of the Partnership Agreement. If the SOW is terminated, the CTP must return all products produced to date. The CTP will return the remaining funds to FEMA for any uncompleted activities under this SOW.

The objective of the PM tasks and activities documented in this SOW is to recognize activities undertaken by CTPs as part of the active process of managing multiple projects. This is broader than individualized project management, which should be covered more directly in any other assigned MASs.

PM tasks and activities cannot result in the production of a Flood Insurance Rate Map (FIRM). Tasks that can be accomplished under this PM SOW are as follow:

State and Local Business Plans and/or Updates (required).

Global Program Management Activities (completed under the PM SOW when the CTP is also funded for tasks in the Flood Risk Project MAS).

Global Outreach for Mapping.

Training to State, Local, Tribal, and Territorial Officials.

Mitigation Planning Technical Assistance.

Staffing.

Technical Pilot Projects.

Mentoring and Best Practices.

Minimal Map Printing.

Coordinated Needs Management Strategy.

Programmatic QA/QC Plans.

CTP Symposium.

State and Local Business Plans and/or Updates (Required)

Intent: State and Local Business Plans and/or updates must be submitted for a partner to receive funding for program management. Plans must describe the capabilities and accomplishments of the partner; explain the CTP’s vision for carrying out or participating in Risk Mapping, Assessment, and Planning (Risk MAP), such as describing how the partner’s activities work toward the vision, goals, and objectives of Risk MAP (including encouraging communities to take action to mitigate risk); include updates from previous years’ activities (if applicable); record flood hazard mapping needs based on physical, climatological, or engineering methodology changes and document these mapping needs to be included in the CNMS Geographic Information System (GIS) data model; and provide recommendations to FEMA regarding future Risk MAP projects within the state or local jurisdiction.

CTPs who also receive an award for the COMS SOW may combine the Business Plan requirements of the PM and COMS awards into a single deliverable with approval from the FEMA Regional Project Officer. The combined Business Plan must include all required elements of the PM Business Plan and the COMS Business Plan.

Global Program Management

(Completed under the PM SOW when the CTP is also funded for tasks in the Flood Risk Project MAS)

Intent: Program management is the active process of managing multiple related projects that need to meet or exceed predefined performance metrics. Specific metrics are defined on a region-by-region basis. It is recommended to include and/or reference specific relevant metrics as appropriate in this document. Efforts across a program will align and work toward meeting Risk MAP goals.

PM activities will typically occur in the areas of integration, scope, schedule, cost, quality, human resources (staffing, training, resource enablement), communication, risk, and/or procurement. Some efforts may extend beyond the scope of work in the SOW or specific project MAS.

The CTP will work with the FEMA Regional Project Officer during the initiation of this activity to determine a PM Plan for implementation.

Global Outreach for Mapping

If conducting a COMS SOW as well, place this activity in COMS and remove/reference it here.

Intent: The Outreach project or activities for a PM SOW enhance the understanding of the overall National Flood Insurance Program (NFIP) flood mapping program. This knowledge includes flood risks and hazard identification. This task does not include the Outreach activities for a specific mapping project that begins during the project Discovery phase and continues through the map production and Post-Preliminary phases.

Note: The communication and outreach activities described in this task supplement or complement the ones in the Community Engagement tasks in the Flood Risk Project MAS. CTPs and the FEMA Regional Office must confirm no duplication of effort in other awards (e.g., grants, cooperative agreements, interagency agreements and contracts).

The main goal for Outreach is to create a climate of understanding and ownership of the mapping process at the State, Local, Tribal, and Territorial levels. Well-planned Outreach activities can ensure a more positive interaction during the Risk MAP process. These outreach activities can also assist FEMA and other members of the Project Management Team in responding to Congressional inquiries. The CTP plans to continue Outreach activities to educate communities on the necessary standards and benefits of developing better flood risk information.

The CTP will work with the FEMA Regional Office during the initiation of this activity to determine or understand the Outreach Plan. The FEMA Regional Office will have access to many outreach tools that have been developed for this process that can be used or customized. All communication with local governments will be done in accordance with Title 44 CFR Section 66 – Consultation with Local Officials.

The Mapping Partner will notify FEMA and all applicable parties of all meetings with community officials at least two weeks before the meeting (with as much notice as possible). FEMA and/or its contractor may or may not attend the community meetings.

Training to State, Local, Tribal, and Territorial Officials

Intent: Develop and provide training to state and local officials during a flood risk project (at the discretion of the Regional Office) that promotes awareness of flood risk and mitigation action.

The CTP must ensure, and must provide documentation when requested by FEMA, that activities funded through this SOW do not replace those funded under other federal grant programs such as Hazard Mitigation Planning or Floodplain Management grant programs.

The CTP must identify whether in-house staff or contractors will give the training.

Training can occur at any time during a Risk MAP project. It may be beneficial to include a series of training activities during a flood risk project. The CTP will coordinate and/or give training to communities and/or individual groups. The CTP will:

Determine target audience and effective methods of communication to reach them.

Advertise to and confirm training participants.

Determine training facility.

Deliver training.

Conduct training evaluations.

Follow up with participants on unresolved issues.

Activities will include planning, developing and delivering trainings or direct support in the areas of:

- Benefit Cost Analysis (BCA) – Support communities to identify, capture and document the necessary data to run a BCA. Explain how to run the FEMA-approved BCA model. Funds cannot be used to run a BCA.

- Building Science – Teach communities about construction issues and opportunities in the identified natural hazard and risk areas.

- Community Capability Development – Help build community capability to sponsor and implement mitigation actions. Activities can include capability assessment; gap analysis; and process, change and project management.

- Community Rating System (CRS) – How to integrate CRS elements into mitigation plans and floodplain ordinances (public information, mapping and regulation, flood damage reduction, warning and response).

- Community Planning – Support communities to assess natural hazards in all facets of community planning (e.g., comprehensive plans, capital improvement plans, stormwater management).

- Grant Application Development – Support communities to develop SOWs, schedules and budgets to successfully apply for a grant. Funds may not be used to develop, submit or execute a grant proposal on behalf of a state, local, tribal, or territorial jurisdiction.

- Mitigation Planning Technical Assistance – Support communities by creating and providing training and technical assistance for achieving mitigation actions. This task cannot fund an activity that is already funded through another federal grant (including the PM SOW). This task should not duplicate assistance available to a community engaged in a Risk MAP project or through a pre- or post-disaster grant funded through the Hazard Mitigation Assistance (HMA) program. Training can be provided at any time during the Risk MAP project. A series of training activities can be provided during a flood risk project.

- Risk Assessment – Support communities as they assess relative risk through Hazus or other methods. Provide technical assistance on how to use a risk assessment tool.

- Risk MAP Data Availability and Tools – Help build community capability to use and understand the regulatory and flood risk components and tools of a Risk MAP project including Flood Risk Products.

- Other – Other activities as discussed with the FEMA Regional Office.

Mitigation Planning Technical Assistance

Intent: Create and distribute products and materials to help State, Local, Tribal, and Territorial jurisdictions form, evaluate, update, and carry out their mitigation plans and strategies. Technical Assistance for Mitigation Planning provided through Risk MAP will focus on building a community’s capability to plan for and reduce risk. Technical Assistance will encourage communities to carry out hazard mitigation plans. It will also help to advance community hazard mitigation actions through the Mitigation Planning Process and Risk MAP projects. This task includes the following steps:

Add new flood hazard and risk information.

Update and refine mitigation strategies, especially as they relate to new flood hazard/risk information.

Train mitigation planning teams.

Add mitigation into current community plans, programs, and policies.

This task will give State, Local, Tribal, and Territorial officials technical assistance for achieving mitigation actions. This task cannot fund the creation or update of a Hazard Mitigation Plan. It also cannot fund an activity that another federal grant already funds (including the COMS SOW). It will not duplicate assistance available to any community engaged in a Risk MAP project or a Hazard Mitigation Assistance planning or project grant.

Staffing

Intent: Provide staff to support Risk MAP Program Management activities. Contractor support may not be engaged for Staffing and Mentoring for this SOW. Staffing and Mentoring must be completed by the CTP.

Technical Pilot Projects

Intent: As defined by and negotiated with the FEMA Regional Office and approved in coordination with FEMA Headquarters. This could include support to Future of Flood Risk Data (FFRD) pilot and validation basin development. Please note that the Letter of Map Revision (LOMR) Review Partner Pilot has its own unique MAS. This PM SOW must not be used for the LOMR Review Partner Pilot Activity.

Mentoring and Best Practices

Intent: Share CTP program experience and related information with peer participants regarding best practices and process improvements.

For this agreement, the CTP will submit at least one written Best Practice to its FEMA Regional Project Officer detailing something that was innovative, cost-saving, enhanced community engagement, or otherwise made the project stand out in a positive way. This best practice will be loaded to the CTP Collaboration Center and CTP Mentoring Network. If this CTP has a COMS SOW as well, this Best Practice can be conducted along with the requirement in that agreement.

Minimal Map Printing

Intent: Print copies of maps for individuals within the CTP’s jurisdiction. Funding for this activity must not be covered under another FEMA grant program and will not exceed $5,000.

Coordinated Needs Management Strategy

Intent: CNMS is a spatial database. Each FEMA Region Service Center (RSC) maintains it as representation of FEMA’s mapped floodplain inventory and a reporting system for New Valid Updated Engineering (NVUE). CNMS is maintained and updated for LOMRs, Discovery, Digital Flood Insurance Rate Map (DFIRM) mapping projects, and expiring CNMS validation miles. The mapping partner will need to work and coordinate with their respective FEMA RSC to make sure the database is updated per FEMA specifications.

The Flood Risk Project MAS should identify the following two optional paragraphs. If a CTP is only doing the CNMS and not the actual Discovery or Mapping Project, this must be coordinated in advance with the FEMA Regional Office and explained in this section.

For this SOW, the CTP will assess and update the CNMS database for request area(s) within the Discovery project footprint after the meeting. This includes stream reaches identified for study/restudy and any areas with remaining needs and/or requests. The mapping partner needs to resolve any discrepancies within CNMS found at Discovery working with the FEMA RSC before the final deliverable.

For this SOW, the CTP will assess and update the CNMS database for all studies affected by the Mapping Project for new or updated studies. This task will need updates and deliverables to the FEMA RSC when the project is funded for Discovery, DFIRM production, Preliminary Issuance, and LFD Issuance. These are four vital updates CNMS needs along a project’s life cycle. The mapping partner will use the CNMS Technical Reference sections (S_Studies_Ln Discovery and Scoping Phase Updates, S_Studies_Ln Preliminary Issuance Phase Update, and S_Studies_Ln LFD Issuance Phase Update) when updating CNMS. The CNMS Technical Reference is available at Technical References for Flood Risk Analysis and Mapping. At each of the three update points, the CNMS database will be submitted to the FEMA RSC for incorporation into the Regional CNMS database. The FEMA RSC FEMA will work with the mapping partner to make sure study information is correct.

For this SOW, the CTP will assess and update the database for all current fiscal year expiring miles and/or unknown miles as of a specified year(s) for evaluation. Expiring miles are any miles with a VALIDATION_STATUS of Valid or Unknown and without a STUDY_TYPE of Being-Studied where the STATUS_DATE is five years or older within that fiscal year. For example, Flood Creek, with a status date of October 10, 2020, will “expire” on calendar year October 10, 2025, or Fiscal Year 25Q1.

During CNMS assessments of existing effective Zone A studies, Base Level Engineering (BLE) data will support directly Refined Zone A Engineering study (A5) validation. For more details about the A5 validation process, refer to “Appendix C: Zone A Study Validation Assessment” in the CNMS Technical Reference. BLE data prepared in accordance with the BLE Analyses and Mapping Guidance (February 2018) will meet the standards for comparison against effective floodplains as described in the CNMS Technical Reference.

All identified detailed (AE, AO, AH) reaches will be assessed using the checks identified in Appendix B: Detailed Study Validation Assessment of the CNMS Technical Reference. They will have appropriate documentation provided. The mapping partner can document the validation findings in check-sheets or within a CNMS database by adding fields.

As with detailed validation, all reaches must include appropriate documentation (see “Appendix B: Detailed Study Validation Assessment” in the CNMS Technical Reference). The mapping partner can document the validation findings in check-sheets or within a CNMS database by adding fields.

In addition to adding new and/or updated studies, as well as the validation checks on expiring miles (if applicable), the mapping partner will update line work to FEMA specifications. This work will be added into the Regional CNMS database. This will include but is not limited to:

Use of topology rules to eliminate incorrect overlaps, multipart features, lines smaller than cluster tolerance, self-overlaps, and self-intersections. Where possible, the mapping partner will work to remove inappropriate dangles and pseudos. The stream network will have connectivity where appropriate.

Maintenance of all attributes as the CNMS Technical Reference states (using the latest available release as a guide).

Use of the most recent CNMS QC tool (ArcGIS Add-in) with no critical errors found. Any secondary errors will need RSC approval. You can get the ArcGIS add-in tool by request to the RSC.

The mapping partner will maintain an archive of all data submitted for not less than three years past the grant closing date.

Programmatic QA/QC Plan

Intent: Form and carry out a programmatic plan for QA and QC of products funded under the Flood Risk Project MAS. Funding for this task does not include QA/QC of products. It only includes forming a plan for QA/QC and the program management aspects that relate to carrying out and monitoring the effectiveness of the plan. Activities will include forming corrective action plans and updates to the QA/QC plan as a result of quality errors that the CTP, FEMA, or FEMA contractors find. Funding for this activity must not be covered under another award. It also will not exceed $10,000.

CTP Symposium

Intent: At the request of the FEMA region, the CTP will travel to and attend the CTP Symposium to participate in discussions, and provide feedback on initiatives and program direction. CTP Symposium attendance from the CTP will occur no more frequently than once per calendar year. Contractor support may not be engaged for the CTP Symposium. In advance of travel, CTP will provide details for their travel to FEMA Regional Office and FEMA Headquarters. If travel to CTP Symposium attendance is not requested by the FEMA region, funds allocated to this activity may be repurposed for other travel related to this SOW with prior approval from the FEMA region.

- Authorized Representative Signatures

Each party has caused this SOW to be executed by its duly authorized representative.

_____________________________________________________________________________________

Glenn Heistand 							Date

Project Manager

Illinois State Water Survey

_____________________________________________________________________________________

John Wethington								Date

FEMA Regional Project Officer

Federal Emergency Management Agency, Region 5

_____________________________________________________________________________________

Julia McCarthy									Date

Mitigation Division Director

Federal Emergency Management Agency, Region 5

- List of Tables

Table 1. Project and Point of Contact Information	2

Table 2. Narrative and Audience	3

Table 3. Task 1 – State and Local Business Plans and/or Updates	6

Table 4. Task 2 – Global Program Management Activities	7

Table 5. Task 3 – Global Outreach for Mapping	8

Table 6. Task 4 – Training to State, Local, Tribal, and Territorial Officials	9

Table 7. Task 5 – Mitigation Planning Technical Assistance	10

Table 8. Task 6 – Directly Funded Staffing	11

Table 9. Task 7 – Technical Pilot Projects	12

Table 10. Task 8 – Mentoring and Best Practices	13

Table 11. Task 9 – Minimal Map Printing	14

Table 12. Task 10 – Coordinated Needs Management Strategy	15

Table 13. Task 11 – Programmatic QA/QC Plans	16

Table 14. Task 12 – CTP Symposium	17

Table 15. Percentage of Time Spent on Tasks for Funded Staff	18

Table 16. Percentage of Time Spent on Tasks for Unfunded Staff	19

Table 17. PM Task Deliverables Schedule	19

Table 18. Performance Measures Targets	20

Table 19. Use of Contractors	22

- Acronyms

BLE	Base Level Engineering

CFR	Code of Federal Regulations

CNMS	Coordinated Needs Management Strategy

COMS	Community Outreach and Mitigation Strategies

CPI	Cost Performance Index

CTP	Cooperating Technical Partner

DFIRM	Digital Flood Insurance Rate Map

FEMA	Federal Emergency Management Agency

FFRD	Future of Flood Risk Data

FIRM	Flood Insurance Rate Map

GIS	Geographic Information System

LFD	Letter of Final Determination

LOMR	Letter of Map Revision

MAS	Mapping Activity Statement

MIP	Mapping Information Platform

NFIP	National Flood Insurance Program

NVUE	New Valid Updated Engineering

PII	Personally Identifiable Information

PM	Program Management

QA/QC	Quality Assurance/Quality Control

RAM	Risk Analysis Management

RAP	RAM Access Portal

RSC	Region Service Center

Risk MAP	Risk Mapping, Assessment, and Planning

SF-PPR	Standard Form-Performance Progress Report

SOW	Statement of Work

SPI	Schedule Performance Index

TA	Technical Assistance

An outcome is an observable and measurable change of knowledge, behavior, skills, and/or efficiency as a result of a CTP project.

An output is a direct, specific, and quantifiable product of CTP activities that lead to/indicate success of the intended outcome, expressed in units of measure that enable quantifiable recording of performance.